## Sheet1
Week | Sprint Goal | Key Tasks | Deliverables
Week 1 | Requirement Gathering & Setup | Finalize requirements, research APIs, set up Git, project structure | Project repo setup, requirement doc
Week 2 | UI/UX Wireframes & Project Skeleton | Design mockups in Figma, basic React pages, navigation bar | Wireframes, UI skeleton
Week 3 | Backend Setup - Spring Boot & Database | Set up Spring Boot, REST APIs, connect PostgreSQL, test API endpoints | Backend boilerplate, DB schema
Week 4 | User Authentication & Registration | Implement login/registration, JWT authentication, role-based access | User login/signup working
Week 5 | Bank API/UPI API Research & Integration Mock | Study bank APIs, design mock integration, simulate UPI transaction data | API research doc, mock APIs
Week 6 | Transaction Fetch Module (Dummy Data) | Create service to fetch/store dummy transaction data in DB | Dummy transaction service
Week 7 | Dashboard UI + Transaction Listing | Build dashboard in React, display transaction history via API | Dashboard with live API data
Week 8 | Edit/Update Transaction Notes | Enable editing/updating descriptions for transactions | Transaction notes editable
Week 9 | Filter/Search/Export Transactions | Implement filters (date, app, amount), export CSV/Excel | Search/filter/export working
Week 10 | Notifications/Reminders Module | Add notifications (spending limit alerts, reminders) | Notifications functional
Week 11 | Security & Testing | Conduct security audit, write JUnit/Mockito tests | Test reports, secured APIs
Week 12 | Deployment & Final Documentation | Deploy on AWS/Heroku, write user manual, final demo | Live deployed project + docs